## Project Overview
DATAFLOW PLATFORM - PROJECT PLANNING
Project Information
Project Name: | DataFlow Data Platform |  | Start Date:
Project Owner: |  |  | Target Go-Live:
Technical Lead: |  |  | Current Phase: | Planning
Last Updated: | 2026-01-15 |  | Status: | In Progress
Project Phases
Phase | Description | Status | Start | End | Owner | Notes
Phase 1 | Core Infrastructure & Authentication | Not Started |  |  |  | Azure setup, Terraform, Auth
Phase 2 | Backend API Foundation | Not Started |  |  |  | FastAPI, Database, Storage
Phase 3 | Frontend Core | Not Started |  |  |  | React app, navigation, auth flow
Phase 4 | User Workspace Features | Not Started |  |  |  | Files, datasets, sharing
Phase 5 | Data Pipeline Engine | Not Started |  |  |  | ETL, transformations
Phase 6 | Collaboration & Approvals | Not Started |  |  |  | Real-time, workflow
Phase 7 | Admin & Monitoring | Not Started |  |  |  | Dashboard, alerts, audit
Phase 8 | Testing & QA | Not Started |  |  |  | Integration, UAT
Phase 9 | Production Deployment | Not Started |  |  |  | Go-live, monitoring

## Frontend Features
Feature ID | Feature Name | Category | Description | Priority | Status | Complexity | Sprint | Assigned To | Dependencies | Notes
FE-001 | Login Screen | Authentication | Microsoft SSO and email/password login | High | Not Started | Medium |  |  | Azure AD setup
FE-002 | Main Navigation | Core | Sidebar navigation with all menu items | High | Not Started | Low
FE-003 | Admin Dashboard | Dashboard | Overview stats, system health, activity feed | High | Not Started | Medium |  |  | BE-001
FE-004 | User Management | Admin | User list, invite, edit, disable users | High | Not Started | Medium |  |  | BE-002
FE-005 | Role Management | Admin | Create/edit roles and permissions | High | Not Started | Medium |  |  | BE-003
FE-006 | Activity Monitor | Admin | Real-time activity feed with filters | Medium | Not Started | Medium |  |  | BE-004
FE-007 | My Workspace | Workspace | Personal dashboard with stats and recent activity | High | Not Started | Medium |  |  | BE-005
FE-008 | My Files | Workspace | File upload, list, preview, delete | High | Not Started | High |  |  | BE-006
FE-009 | My Datasets | Workspace | Dataset list with status indicators | High | Not Started | Medium |  |  | BE-007
FE-010 | Shared With Me | Workspace | View shared files/datasets | High | Not Started | Medium |  |  | BE-008
FE-011 | Dataset Viewer | Data | View dataset with schema, preview, metadata | High | Not Started | High |  |  | BE-009
FE-012 | Dataset Editor | Data | Edit queries, transformations | High | Not Started | High |  |  | BE-010
FE-013 | Create Dataset Modal | Data | Create dataset from query/upload/existing | High | Not Started | High |  |  | BE-011
FE-014 | Data Preview Grid | Data | Spreadsheet-like data preview | High | Not Started | High |  |  |  | Consider AG Grid
FE-015 | Query Editor | Data | SQL editor with syntax highlighting | High | Not Started | High |  |  |  | Monaco Editor
FE-016 | Share Modal | Collaboration | Share with users/groups, set permissions | High | Not Started | Medium |  |  | BE-012
FE-017 | Comments Panel | Collaboration | Add/view comments on datasets | Medium | Not Started | Medium |  |  | BE-013
FE-018 | Submit for Approval | Workflow | Approval submission form | Medium | Not Started | Medium |  |  | BE-014
FE-019 | Approval Queue | Workflow | Approver's pending reviews list | Medium | Not Started | Medium |  |  | BE-015
FE-020 | Review Dataset | Workflow | Approval review interface | Medium | Not Started | High |  |  | BE-016
FE-021 | Data Connections | Admin | Manage external data connections | Medium | Not Started | High |  |  | BE-017
FE-022 | Pipeline Builder | Pipelines | Visual pipeline creation | Low | Not Started | Very High |  |  | BE-018 | Phase 2
FE-023 | Pipeline Monitor | Pipelines | View running/completed pipelines | Medium | Not Started | Medium |  |  | BE-019
FE-024 | Notifications | Core | Notification center and toasts | Medium | Not Started | Medium |  |  | BE-020
FE-025 | Settings Page | Core | User preferences and settings | Low | Not Started | Low |  |  | BE-021
FE-026 | Data Catalog | Discovery | Browse published datasets | Medium | Not Started | Medium |  |  | BE-022
FE-027 | Search | Discovery | Global search across all content | Medium | Not Started | High |  |  | BE-023
FE-028 | Version History | Data | View/restore dataset versions | Medium | Not Started | Medium |  |  | BE-024
FE-029 | Audit Log Viewer | Admin | View detailed audit logs | Low | Not Started | Medium |  |  | BE-025
FE-030 | Dark/Light Theme | Core | Theme toggle functionality | Low | Not Started | Low

## Backend Features
Feature ID | Feature Name | Category | Description | Priority | Status | Complexity | Sprint | Assigned To | API Endpoints | Notes
BE-001 | Health & Stats API | Core | System health, dashboard statistics | High | Not Started | Low |  |  | GET /api/health, GET /api/stats
BE-002 | User CRUD API | Auth | Create, read, update, delete users | High | Not Started | Medium |  |  | GET/POST/PUT/DELETE /api/users
BE-003 | Role Management API | Auth | Role and permission management | High | Not Started | Medium |  |  | /api/roles, /api/permissions
BE-004 | Activity Logging | Core | Log all user actions, retrieve activity | High | Not Started | Medium |  |  | GET /api/activity
BE-005 | Workspace Stats API | Workspace | User's file/dataset counts | High | Not Started | Low |  |  | GET /api/workspace/stats
BE-006 | File Upload Service | Storage | Upload files to Azure Blob | High | Not Started | High |  |  | POST /api/files/upload | Chunked upload
BE-007 | Dataset CRUD API | Data | Dataset management endpoints | High | Not Started | High |  |  | /api/datasets/*
BE-008 | Sharing API | Collaboration | Share resources with users/groups | High | Not Started | Medium |  |  | /api/shares/*
BE-009 | Dataset Read API | Data | Get dataset with preview data | High | Not Started | Medium |  |  | GET /api/datasets/{id}
BE-010 | Dataset Update API | Data | Update dataset definition/query | High | Not Started | High |  |  | PUT /api/datasets/{id}
BE-011 | Dataset Creation | Data | Create dataset from various sources | High | Not Started | Very High |  |  | POST /api/datasets | Query execution
BE-012 | Share Management | Collaboration | Manage sharing permissions | High | Not Started | Medium |  |  | /api/datasets/{id}/share
BE-013 | Comments API | Collaboration | CRUD for comments | Medium | Not Started | Low |  |  | /api/comments/*
BE-014 | Approval Submit | Workflow | Submit dataset for approval | Medium | Not Started | Medium |  |  | POST /api/approvals
BE-015 | Approval Queue API | Workflow | Get pending approvals | Medium | Not Started | Low |  |  | GET /api/approvals
BE-016 | Approval Review | Workflow | Submit approval decision | Medium | Not Started | Medium |  |  | POST /api/approvals/{id}/review
BE-017 | Connections API | Integration | Manage data source connections | Medium | Not Started | High |  |  | /api/connections/*
BE-018 | Pipeline Engine | Pipelines | Execute data pipelines | Low | Not Started | Very High |  |  | /api/pipelines/* | Phase 2
BE-019 | Pipeline Status API | Pipelines | Pipeline execution status | Medium | Not Started | Medium |  |  | GET /api/pipelines/{id}/status
BE-020 | Notifications API | Core | User notifications | Medium | Not Started | Medium |  |  | /api/notifications/*
BE-021 | Settings API | Core | User preferences | Low | Not Started | Low |  |  | /api/settings/*
BE-022 | Catalog API | Discovery | Published datasets catalog | Medium | Not Started | Medium |  |  | GET /api/catalog
BE-023 | Search API | Discovery | Full-text search | Medium | Not Started | High |  |  | GET /api/search
BE-024 | Version History API | Data | Dataset version management | Medium | Not Started | Medium |  |  | /api/datasets/{id}/versions
BE-025 | Audit Log API | Admin | Detailed audit log retrieval | Low | Not Started | Medium |  |  | GET /api/audit
BE-026 | Azure AD Integration | Auth | MSAL authentication | High | Not Started | High
BE-027 | Blob Storage Service | Storage | Azure Blob operations | High | Not Started | Medium
BE-028 | SQL Server Service | Storage | Database operations | High | Not Started | Medium
BE-029 | Parquet Conversion | Data | Convert data to Parquet format | High | Not Started | High |  |  |  | PyArrow
BE-030 | WebSocket Server | Collaboration | Real-time collaboration | Low | Not Started | Very High |  |  | WS /ws/* | Phase 2

## Technology Stack
Category | Technology | Version | Purpose | License | Documentation | Decision Rationale | Alternatives Considered
Frontend | React | 18.x | UI Framework | MIT | https://react.dev | Industry standard, large ecosystem | Vue, Angular, Svelte
Frontend | TypeScript | 5.x | Type-safe JavaScript | Apache 2.0 | https://typescriptlang.org | Better code quality, IDE support | JavaScript
Frontend | Vite | 5.x | Build tool | MIT | https://vitejs.dev | Fast HMR, modern tooling | Webpack, CRA
Frontend | TailwindCSS | 4.x | CSS Framework | MIT | https://tailwindcss.com | Utility-first, highly customizable | Bootstrap, MUI
Frontend | React Router | 6.x | Routing | MIT | https://reactrouter.com | Standard React routing | TanStack Router
Frontend | TanStack Query | 5.x | Data fetching | MIT | https://tanstack.com/query | Caching, server state management | SWR, RTK Query
Frontend | Zustand | 4.x | State management | MIT | https://zustand-demo.pmnd.rs | Simple, minimal boilerplate | Redux, Jotai
Frontend | Monaco Editor | Latest | Code editor | MIT | https://microsoft.github.io/monaco-editor/ | VS Code editor component | CodeMirror, Ace
Frontend | AG Grid | Latest | Data grid | Commercial | https://ag-grid.com | Best-in-class data grid | TanStack Table
Frontend | Recharts | 2.x | Charts | MIT | https://recharts.org | React-native charting | Chart.js, D3
Backend | Python | 3.11+ | Primary language | PSF | https://python.org | Data processing, Azure SDKs | Node.js, Go
Backend | FastAPI | 0.100+ | API Framework | MIT | https://fastapi.tiangolo.com | Modern, async, auto-docs | Flask, Django
Backend | SQLAlchemy | 2.x | ORM | MIT | https://sqlalchemy.org | Flexible ORM, raw SQL support | Peewee, Django ORM
Backend | Pydantic | 2.x | Data validation | MIT | https://pydantic.dev | Type hints, FastAPI integration | Marshmallow
Backend | PyArrow | Latest | Parquet handling | Apache 2.0 | https://arrow.apache.org/docs/python/ | Fast Parquet read/write | Pandas
Backend | Pandas | 2.x | Data manipulation | BSD | https://pandas.pydata.org | Data transformation | Polars
Backend | Uvicorn | Latest | ASGI Server | BSD | https://uvicorn.org | High performance async | Gunicorn
Backend | Alembic | Latest | DB Migrations | MIT | https://alembic.sqlalchemy.org | SQLAlchemy migrations
Azure | Azure AD (Entra ID) | N/A | Authentication | N/A | https://learn.microsoft.com/azure/active-directory/ | Corporate SSO, security | Auth0, Okta
Azure | Azure Static Web Apps | N/A | Frontend hosting | N/A | https://azure.microsoft.com/services/app-service/static/ | Easy deployment, CDN | Azure CDN, Blob static
Azure | Azure App Service | N/A | Backend hosting | N/A | https://azure.microsoft.com/services/app-service/ | Managed containers | AKS, Container Apps
Azure | Azure SQL Server | N/A | Relational database | N/A | https://azure.microsoft.com/services/sql-database/ | Managed SQL Server | PostgreSQL, CosmosDB
Azure | Azure Blob Storage | N/A | File storage | N/A | https://azure.microsoft.com/services/storage/blobs/ | Scalable object storage | Azure Files
Azure | Azure Key Vault | N/A | Secrets management | N/A | https://azure.microsoft.com/services/key-vault/ | Secure secret storage | HashiCorp Vault
Azure | Application Insights | N/A | Monitoring | N/A | https://learn.microsoft.com/azure/azure-monitor/app/app-insights-overview | APM, logging | Datadog, New Relic
DevOps | GitHub Actions | N/A | CI/CD | N/A | https://docs.github.com/actions | GitHub integration | Azure DevOps
DevOps | Terraform | 1.5+ | Infrastructure as Code | MPL 2.0 | https://terraform.io | Multi-cloud IaC | Bicep, ARM
DevOps | Docker | Latest | Containerization | Apache 2.0 | https://docker.com | Standard containerization | Podman
Testing | Pytest | 7.x | Python testing | MIT | https://pytest.org | Standard Python testing | unittest
Testing | Vitest | Latest | Frontend testing | MIT | https://vitest.dev | Vite-native testing | Jest
Testing | Playwright | Latest | E2E testing | Apache 2.0 | https://playwright.dev | Cross-browser E2E | Cypress, Selenium

## ETL Operations
ETL ID | Operation Name | Type | Source | Destination | Schedule | Priority | Status | Owner | Description | Dependencies | Notes
ETL-001 | Daily Sales Import | Batch | SAP | Azure SQL | Daily 02:00 | High | Planned |  | Import daily sales transactions from SAP | SAP connection
ETL-002 | Customer Data Sync | Batch | Salesforce | Azure SQL | Daily 03:00 | High | Planned |  | Sync customer master data | Salesforce API
ETL-003 | Product Catalog Update | Batch | ERP System | Azure SQL | Daily 04:00 | Medium | Planned |  | Update product information | ERP connection
ETL-004 | Inventory Snapshot | Batch | Warehouse System | Azure Blob | Hourly | High | Planned |  | Hourly inventory levels snapshot | Warehouse API
ETL-005 | Financial Data Load | Batch | Finance System | Azure SQL | Monthly | High | Planned |  | Monthly financial close data | Finance system access
ETL-006 | Web Analytics Import | Batch | Google Analytics | Azure SQL | Daily 01:00 | Medium | Planned |  | Import web traffic data | GA API credentials
ETL-007 | Email Campaign Metrics | Batch | Mailchimp | Azure SQL | Daily 05:00 | Low | Planned |  | Email campaign performance data | Mailchimp API
ETL-008 | Data Quality Checks | Batch | Azure SQL | Azure SQL | Daily 06:00 | High | Planned |  | Run data quality validation rules | All daily loads
ETL-009 | Aggregation Jobs | Batch | Azure SQL | Azure SQL | Daily 07:00 | Medium | Planned |  | Create daily/weekly/monthly aggregates | ETL-008
ETL-010 | Archive Old Data | Batch | Azure SQL | Azure Blob | Weekly Sun 00:00 | Low | Planned |  | Archive data older than 2 years
ETL-011 | Real-time Events | Streaming | Event Hub | Azure SQL | Real-time | High | Planned |  | Process real-time user events | Event Hub setup | Phase 2
ETL-012 | CDC Processing | CDC | Source DBs | Azure SQL | Near real-time | Medium | Planned |  | Change data capture from source systems | CDC setup | Phase 2
ETL-013 | Data Lake Sync | Batch | Azure SQL | Data Lake | Daily 08:00 | Medium | Planned |  | Sync processed data to data lake | Data Lake setup
ETL-014 | External API Refresh | Batch | Various APIs | Azure SQL | Varies | Medium | Planned |  | Refresh data from external APIs | API credentials
ETL-015 | Report Data Prep | Batch | Azure SQL | Azure SQL | Daily 09:00 | High | Planned |  | Prepare data marts for reporting | ETL-009

## Data Sources
Source ID | Source Name | Type | System | Connection Method | Frequency | Data Volume | Owner | Status | Credentials Location | Notes
DS-001 | SAP ERP | Database | SAP HANA | ODBC/RFC | Daily | ~5GB/day |  | Planned | Key Vault | Primary ERP system
DS-002 | Salesforce | API | Salesforce | REST API | Daily | ~500MB/day |  | Planned | Key Vault | CRM data
DS-003 | SQL Server (Legacy) | Database | On-prem SQL | ODBC | Daily | ~2GB/day |  | Planned | Key Vault | Legacy system data
DS-004 | Azure SQL (Platform) | Database | Azure SQL | Direct | Real-time | N/A |  | Planned | Managed Identity | Platform database
DS-005 | Azure Blob Storage | Storage | Azure Blob | SDK | Real-time | N/A |  | Planned | Managed Identity | File storage
DS-006 | Google Analytics | API | GA4 | REST API | Daily | ~100MB/day |  | Planned | Key Vault | Web analytics
DS-007 | Mailchimp | API | Mailchimp | REST API | Daily | ~50MB/day |  | Planned | Key Vault | Email marketing
DS-008 | Warehouse System | API | WMS | REST API | Hourly | ~200MB/day |  | Planned | Key Vault | Inventory data
DS-009 | Finance System | Database | Oracle | ODBC | Monthly | ~1GB/month |  | Planned | Key Vault | Financial data
DS-010 | Manual Uploads | File | User uploads | Blob Upload | Ad-hoc | Varies |  | Active | N/A | CSV, Excel, JSON

## Database Schema
Table Name | Category | Description | Key Columns | Relationships | Estimated Rows | Status | Notes
users | Auth | User accounts | id, email, azure_ad_id, name, role_id | roles, files, datasets | 1,000+ | Designed
roles | Auth | User roles | id, name, description, permissions | users | 10 | Designed
permissions | Auth | Available permissions | id, name, category, description | role_permissions | 50+ | Designed
role_permissions | Auth | Role-permission mapping | role_id, permission_id | roles, permissions | 500+ | Designed
files | Storage | Uploaded files metadata | id, user_id, name, path, size, type | users, file_shares | 100,000+ | Designed
datasets | Data | Dataset definitions | id, name, owner_id, status, version, query | users, dataset_versions | 10,000+ | Designed
dataset_versions | Data | Dataset version history | id, dataset_id, version, path, schema | datasets | 50,000+ | Designed
shares | Collaboration | Sharing permissions | id, resource_type, resource_id, user_id, permission | users, datasets, files | 50,000+ | Designed
share_links | Collaboration | Shareable links | id, resource_id, link_type, permission | datasets, files | 10,000+ | Designed
comments | Collaboration | Comments on resources | id, resource_id, user_id, content, parent_id | users, datasets | 100,000+ | Designed
dataset_sessions | Collaboration | Active editing sessions | id, dataset_id, user_id, session_type | users, datasets | 100 | Designed | Real-time tracking
approval_requests | Workflow | Approval submissions | id, dataset_id, requested_by, status | users, datasets | 5,000+ | Designed
approval_reviews | Workflow | Approval decisions | id, request_id, reviewer_id, decision | approval_requests, users | 10,000+ | Designed
notifications | Core | User notifications | id, user_id, type, title, message, read | users | 500,000+ | Designed
audit_log | Core | Audit trail | id, user_id, action, resource_type, resource_id, timestamp | users | 10,000,000+ | Designed | Partitioned by date
connections | Integration | External data connections | id, name, type, config, credentials_ref |  | 50 | Designed | Encrypted config
pipelines | ETL | Pipeline definitions | id, name, config, schedule, owner_id | users, pipeline_runs | 100+ | Designed
pipeline_runs | ETL | Pipeline execution history | id, pipeline_id, status, started_at, completed_at | pipelines | 100,000+ | Designed
settings | Core | User/system settings | id, user_id, key, value | users | 10,000+ | Designed

## API Endpoints
Endpoint | Method | Category | Description | Auth Required | Request Body | Response | Status | Notes
/api/health | GET | Core | Health check | No | - | {status, version} | Planned
/api/stats | GET | Core | Dashboard statistics | Yes | - | {users, datasets, pipelines...} | Planned
/api/auth/login | POST | Auth | User login | No | {email, password} | {token, user} | Planned
/api/auth/azure | POST | Auth | Azure AD login | No | {azure_token} | {token, user} | Planned
/api/auth/me | GET | Auth | Current user info | Yes | - | {user} | Planned
/api/users | GET | Users | List users | Yes (Admin) | ?page, ?search | {users[], total} | Planned
/api/users | POST | Users | Create user | Yes (Admin) | {email, name, role_id} | {user} | Planned
/api/users/{id} | GET | Users | Get user | Yes | - | {user} | Planned
/api/users/{id} | PUT | Users | Update user | Yes (Admin) | {name, role_id, status} | {user} | Planned
/api/users/{id} | DELETE | Users | Delete user | Yes (Admin) | - | {success} | Planned
/api/roles | GET | Roles | List roles | Yes | - | {roles[]} | Planned
/api/roles | POST | Roles | Create role | Yes (Admin) | {name, permissions[]} | {role} | Planned
/api/roles/{id} | PUT | Roles | Update role | Yes (Admin) | {name, permissions[]} | {role} | Planned
/api/activity | GET | Activity | Get activity feed | Yes | ?type, ?user, ?date | {activities[]} | Planned
/api/workspace/stats | GET | Workspace | User workspace stats | Yes | - | {files, datasets, shared} | Planned
/api/files | GET | Files | List user files | Yes | ?page, ?search | {files[], total} | Planned
/api/files/upload | POST | Files | Upload file | Yes | multipart/form-data | {file} | Planned | Chunked
/api/files/{id} | GET | Files | Get file info | Yes | - | {file} | Planned
/api/files/{id} | DELETE | Files | Delete file | Yes | - | {success} | Planned
/api/files/{id}/download | GET | Files | Download file | Yes | - | binary | Planned
/api/datasets | GET | Datasets | List datasets | Yes | ?status, ?page | {datasets[], total} | Planned
/api/datasets | POST | Datasets | Create dataset | Yes | {name, source, query...} | {dataset} | Planned
/api/datasets/{id} | GET | Datasets | Get dataset | Yes | - | {dataset, preview} | Planned
/api/datasets/{id} | PUT | Datasets | Update dataset | Yes | {name, query...} | {dataset} | Planned
/api/datasets/{id} | DELETE | Datasets | Delete dataset | Yes | - | {success} | Planned
/api/datasets/{id}/preview | GET | Datasets | Get data preview | Yes | ?limit, ?offset | {rows[], schema} | Planned
/api/datasets/{id}/versions | GET | Datasets | Version history | Yes | - | {versions[]} | Planned
/api/datasets/{id}/share | POST | Sharing | Share dataset | Yes | {user_id, permission} | {share} | Planned
/api/datasets/{id}/share | GET | Sharing | Get collaborators | Yes | - | {shares[]} | Planned
/api/datasets/{id}/share/{user_id} | DELETE | Sharing | Remove share | Yes | - | {success} | Planned
/api/datasets/{id}/comments | GET | Comments | Get comments | Yes | - | {comments[]} | Planned
/api/datasets/{id}/comments | POST | Comments | Add comment | Yes | {content, parent_id?} | {comment} | Planned
/api/approvals | GET | Workflow | List approval requests | Yes | ?status | {requests[]} | Planned
/api/approvals | POST | Workflow | Submit for approval | Yes | {dataset_id, targets[], notes} | {request} | Planned
/api/approvals/{id} | GET | Workflow | Get approval details | Yes | - | {request, reviews[]} | Planned
/api/approvals/{id}/review | POST | Workflow | Submit review | Yes | {decision, comments} | {review} | Planned
/api/catalog | GET | Discovery | Browse data catalog | Yes | ?category, ?search | {datasets[]} | Planned
/api/search | GET | Discovery | Global search | Yes | ?q | {results[]} | Planned
/api/connections | GET | Admin | List connections | Yes (Admin) | - | {connections[]} | Planned
/api/connections | POST | Admin | Create connection | Yes (Admin) | {name, type, config} | {connection} | Planned
/api/notifications | GET | Core | Get notifications | Yes | ?unread | {notifications[]} | Planned
/api/notifications/{id}/read | POST | Core | Mark as read | Yes | - | {success} | Planned

## Environments
Environment | Purpose | URL | Azure Resource Group | Database | Storage Account | Deployment | Access | Notes
Local | Development | http://localhost:5173 | N/A | Local/Docker | Azurite | Manual | Developers
Dev | Development testing | https://dataflow-dev.azurestaticapps.net | rg-dataflow-dev | sql-dataflow-dev | stdataflowdev | Auto (PR) | Team
Test | QA/Testing | https://dataflow-test.azurestaticapps.net | rg-dataflow-test | sql-dataflow-test | stdataflowtest | Manual | QA Team
Staging | Pre-production | https://dataflow-staging.azurestaticapps.net | rg-dataflow-staging | sql-dataflow-staging | stdataflowstaging | Manual | Selected users
Production | Live | https://dataflow.company.com | rg-dataflow-prod | sql-dataflow-prod | stdataflowprod | Manual (approval) | All users

## Risks & Issues
ID | Type | Title | Description | Impact | Probability | Severity | Mitigation | Owner | Status | Date Raised | Date Resolved
R-001 | Risk | Azure AD Integration Complexity | Integration with existing Azure AD may require custom configuration | High | Medium | High | Early spike to validate integration approach |  | Open
R-002 | Risk | Data Volume Performance | Large datasets may cause performance issues | High | Medium | High | Implement pagination, lazy loading, caching |  | Open
R-003 | Risk | Legacy System Connectivity | Connecting to legacy on-prem systems | Medium | High | High | Identify systems early, plan hybrid connectivity |  | Open
R-004 | Risk | Team Learning Curve | Team may need time to learn new technologies | Medium | Medium | Medium | Training sessions, documentation, pair programming |  | Open
R-005 | Risk | Scope Creep | Additional features requested during development | High | High | High | Clear MVP definition, change control process |  | Open
R-006 | Risk | Data Security Compliance | Meeting corporate security requirements | High | Low | Medium | Early security review, compliance checklist |  | Open
I-001 | Issue
I-002 | Issue

## Team & RACI
Name | Role | Responsibilities | Email | Availability | Skills | Notes
| Project Owner | Overall accountability, stakeholder management
| Technical Lead | Architecture decisions, code review, technical guidance
| Frontend Developer | React development, UI/UX implementation
| Backend Developer | API development, database, Azure services
| Data Engineer | ETL pipelines, data modeling, integrations
| QA Engineer | Testing strategy, test automation
| DevOps Engineer | CI/CD, infrastructure, monitoring
| Business Analyst | Requirements, user acceptance testing

## Decisions Log
Decision ID | Date | Decision | Context/Options Considered | Rationale | Made By | Impact | Status
D-001 |  | Use React + TypeScript for frontend | React vs Vue vs Angular | Larger ecosystem, team familiarity, TypeScript support |  | Frontend architecture | Approved
D-002 |  | Use FastAPI for backend | FastAPI vs Flask vs Django | Modern async, auto-documentation, performance |  | Backend architecture | Approved
D-003 |  | Store datasets as Parquet in Blob Storage | Parquet vs CSV vs Delta Lake | Columnar format, compression, schema support |  | Data storage | Approved
D-004 |  | Use Terraform for infrastructure | Terraform vs Bicep vs ARM | Multi-cloud support, team familiarity |  | Infrastructure | Approved
D-005 |  | Use Azure Static Web Apps for frontend hosting | Static Web Apps vs CDN vs App Service | Built-in CI/CD, staging environments, cost |  | Deployment | Approved
D-006 | [6 empty] | Pending
D-007 | [6 empty] | Pending

## Meeting Notes
Date | Meeting Type | Attendees | Agenda | Discussion Points | Decisions Made | Action Items | Next Meeting

## Glossary
Term | Definition | Context | Related Terms
Dataset | A saved, versioned, queryable data asset stored in the platform | Core concept | File, Version
Workspace | A user's personal area containing their files, datasets, and shared items | UI/UX | Dashboard
ETL | Extract, Transform, Load - process of moving and transforming data | Data Engineering | Pipeline, Batch
Pipeline | An automated sequence of data processing steps | Data Engineering | ETL, Job
Parquet | Columnar storage file format optimized for analytics | Data Storage | Dataset
RBAC | Role-Based Access Control - permission system based on roles | Security | Permission, Role
SSO | Single Sign-On - authentication method using corporate credentials | Authentication | Azure AD
Blob Storage | Azure object storage service for unstructured data | Azure | Storage Account
MSAL | Microsoft Authentication Library - Azure AD authentication SDK | Authentication | Azure AD, OAuth
Approval Workflow | Process requiring review before publishing datasets | Governance | Review, Publish
Data Catalog | Searchable inventory of published datasets | Discovery | Dataset, Metadata
Version | A point-in-time snapshot of a dataset | Data Management | Dataset, History
Share | Granting access to a file or dataset to other users | Collaboration | Permission
Draft | A dataset that is being worked on but not yet published | Workflow | Published, Pending